## Summary
Power BI project summary
What you asked for and what was delivered. Data: Sales Dashboard model, 1-8 October 2026 (8 transactions). Summary prepared 20 October 2026.
Sr . No | What you provided | What was delivered | Output | Status
1 | Connect with Power BI Report | Connected to the open Power BI Desktop file, Sales Dashboard | Live connection | Done
2 | Create date table | Calculated Date table (16 columns, all of 2026), marked as the date table, with sort orders and a relationship to Sales | Model change | Done and tested
3 | Is Power BI report joined? | Checked the model: 4 active relationships, with Sales as the central table | Model check | Done
4 | Create basic measures and calculations | 16 core measures: sales, cost, profit, margin %, orders, averages, YTD | Model change | Done and tested
5 | Create 100+ time intelligence functions | 155 more measures in 12 display folders, bringing the total to 171 | Model change | Done and tested
6 | Add comments in each measure | PURPOSE and LOGIC comments written inside every DAX formula (171 of 171) | Model change | Done and verified
7 | Write clear description for all measures and columns | Descriptions on 171 measures, 33 columns and 5 tables | Model change | Done and verified
8 | Create end-to-end report as PDF | 9-page analyst report: model, data quality, sales, product, customer and region analysis, recommendations | Sales_Performance_Report.pdf | Done
9 | Create Power BI visualization | Interactive web dashboard with slicers and cross-filtering. It is separate from your Power BI file | Published web page | Done
10 | Uploaded Sales_Dashboard.pbix: add visuals | Added a dashboard page with 17 visuals (6 cards, 4 slicers, 7 charts and a table) | Sales_Dashboard_with_Visuals.pbix | Done

## Measure Groups
Measure library
All measures sit on the Sales table, grouped by display folder.
Group (display folder) | Measures | Examples
Core measures | 16 | Total Sales, Total Cost, Total Profit, Profit Margin %, Order Count, Average Order Value, Sales YTD
TI 0 Helpers | 5 | Data Last Date, Anchor Date, Days With Sales
TI 1 To-Date | 10 | Sales WTD; Quantity, Profit and Orders MTD, QTD, YTD
TI 2 Prior Period | 20 | Prior Quarter, Month, Week, Day, Year
TI 3 Variance | 21 | YoY, QoQ, MoM, WoW and DoD change and %
TI 4 Rolling | 24 | Rolling 7D, 30D, 90D, 3M, 6M, 12M
TI 5 Running Total | 6 | Sales Running Total, Running Total % of Total
TI 6 Period Totals | 8 | Full Year, Quarter, Month; % of each
TI 7 First-Last Day | 6 | Sales on first or last day of month, quarter, year
TI 8 Averages and Extremes | 16 | Avg Daily, Monthly, Weekly; Best Day; Weekend %
TI 9 PY To-Date and Trends | 14 | YTD, MTD, QTD vs prior year; moving averages
TI 10 Fiscal Year (Apr-Mar) | 10 | Sales FYTD, FYTD YoY %, Fiscal Year Label
TI 11 Latest and Relative | 15 | Latest Day, Today, Last 30 Days, This Month
Total | 171
Counts taken from the model's display folders; the total matches the 171 measures confirmed by query.

## Open Items
Open items
Things to check before sharing or relying on the work.
Item | Why it matters | What to do
Rebuilt .pbix not tested | I cannot open Power BI Desktop files, so I could not confirm it opens or that the visuals look right | Open Sales_Dashboard_with_Visuals.pbix. If there is an error, click Copy details to clipboard and send it to me
Confirm measures are in your saved file | Power BI Desktop restarted several times during the work | Press Ctrl+S in Power BI Desktop and check that the measures are present
Only 8 days of data | Year-over-year, prior-period and rolling 12-month measures are blank until earlier data is loaded | Load at least 13 months of history
Currency not labelled | The model stores no currency, so amounts are shown as plain numbers | Add a currency format if needed
LinkedIn claim about visuals | The visuals file is unconfirmed | Hold the claim that Claude builds report visuals until the file is verified